## Start Here
Capability Builders Cohort Planner
How a cohort is structured, and a planner to pick your team's first project and estimate what fixing it is worth.
How to use it
| Step 1 | Read How It Works. Six hours of live facilitation, your team's own real problem, Green Belt certification at the end.
| Step 2 | On Schedule, enter a kickoff date and pick the format. The session dates and agenda fill in.
| Step 3 | On Project Picker, list the bottlenecks your office deals with and score each one. The sheet ranks them.
| Step 4 | On Team, list who would be in the cohort. It checks that supervisors, managers, and staff are all in the room.
| Step 5 | On Impact Estimate, enter volumes and times for the top pick to see staff hours freed and days saved for students.
What each tab does
| How It Works | The cohort structure in plain language.
| Schedule | Session dates and what happens in each session, from your kickoff date and format.
| Project Picker | Weighted scoring to choose the first project.
| Team | Who is in the cohort, by level.
| Impact Estimate | What fixing the top project is worth.
| Formula Guide | Every formula, explained.
Color key
| Tan cell | Your input. Type over the example values.
| White cell | Formula. Don't type here, it updates on its own. The Formula Guide tab lists every one.
The example values are made up to show how the tool works. They are not benchmarks.
Change Maven LLC ¦ mavenshift.co ¦ change_maven@outlook.com ¦ 217-691-6138

## How It Works
How the cohort works
A facilitated Lean Six Sigma program built around your team's own problem.
| Live time | 6 hours of live facilitation, as three 2-hour sessions or six 1-hour sessions.
| The project | Your team picks a real bottleneck in its own office, not a case study from another school.
| The method | DMAIC. Define, Measure, Analyze, Improve, Control. Taught as the team works the real problem.
| Between sessions | Teams work the project on their own and log progress in Kure, GLSS's certified project platform, with support available.
| Who's in the room | Supervisors, managers, and individual contributors together. Leaders practice breaking big problems into small changes, staff own a real piece of the work.
| What you keep | A finished improvement project, Green Belt certification for the people who complete it, and a team that can run the next one without an outside consultant.
Change Maven LLC ¦ mavenshift.co ¦ change_maven@outlook.com ¦ 217-691-6138

## Schedule
Schedule
Enter a kickoff date and format. Dates land on weekdays.
Kickoff date | 2027-01-19
Format | Three 2-hour sessions
Weeks between sessions | 3 |  | Three or four weeks works well for the 3-session format, two weeks for the 6-session format.
Number of sessions | 3
Hours per session | 2
Total live hours | 6
Final session | 2027-03-02
Program length (weeks) | 6
Session | Date | Hours | What happens live | Team work before the next session | # | 3-session agenda | 6-session agenda | 3-session team work | 6-session team work
1 | 2027-01-19 | 2 | Define and Measure. Lean, continuous improvement, and Six Sigma basics. The team picks its real project and opens Define and Measure. | Map the current process and collect baseline data in Kure. | 1 | Define and Measure. Lean, continuous improvement, and Six Sigma basics. The team picks its real project and opens Define and Measure. | Lean and Six Sigma basics. Choose the project and open Define. | Map the current process and collect baseline data in Kure. | Write the project charter and problem statement.
2 | 2027-02-09 | 2 | Analyze and Improve. Review what the team found, work through where it got stuck, then open Analyze and Improve. | Test root causes and pilot the improvement. | 2 | Analyze and Improve. Review what the team found, work through where it got stuck, then open Analyze and Improve. | Measure. Set the baseline and decide how it will be tracked. | Test root causes and pilot the improvement. | Collect baseline data.
3 | 2027-03-02 | 2 | Control and certification. Lock in the fix, carry it through Control, and complete Green Belt certification. | Hand the control plan to the process owner. | 3 | Control and certification. Lock in the fix, carry it through Control, and complete Green Belt certification. | Analyze. Find the root causes behind the delay. | Hand the control plan to the process owner. | Test the top root causes with data.
[5 empty] | 4 |  | Improve. Choose and pilot the fix. |  | Run the pilot and measure the results.
[5 empty] | 5 |  | Control. Build the control plan so the gain holds. |  | Finish the control plan and the owner handoff.
[5 empty] | 6 |  | Results review and Green Belt certification. |  | Present results to leadership.
Agenda text in H:K is editable. The schedule on the left pulls from it.

## Project Picker
Project Picker
Score each candidate 1 (low) to 5 (high) on every criterion. Weights in row 5 say what matters most to you.
Teams | 1 | How many project teams the cohort will run. That many top-ranked projects get marked Pick.
# | Candidate problem | Impact on students | Staff time freed | Data is available | Fix is within the team's control | Leadership will back it | Weighted score | Rank | Pick?
| Weight (1 to 3) | 3 | 2 | 2 | 3 | 2
1 | Financial aid verification takes too long | 5 | 4 | 4 | 4 | 4 | 51 | 1 | Pick
2 | Transfer credit evaluations sit in a backlog | 4 | 4 | 3 | 3 | 3 | 41 | 4
3 | Advising appointment no-shows | 3 | 3 | 4 | 3 | 3 | 38 | 5
4 | Transcript requests take days to process | 3 | 3 | 4 | 5 | 3 | 44 | 3
5 | Incomplete admissions applications aren't followed up | 5 | 2 | 3 | 4 | 5 | 47 | 2
6 | Course schedule conflicts at registration | 4 | 2 | 3 | 2 | 3 | 34 | 6
| Top pick | Financial aid verification takes too long
| Highest possible score | 60
| Top pick as share of the highest possible | 85%

## Team
Team
Who's in the cohort. Mix levels on purpose.
Name | Role | Level | Department | Level | People
Team member A | Director of Financial Aid | Manager | Financial Aid | Supervisor | 2
Team member B | Financial Aid Counselor | Individual contributor | Financial Aid | Manager | 1
Team member C | Financial Aid Counselor | Individual contributor | Financial Aid | Individual contributor | 3
Team member D | Assistant Registrar | Supervisor | Registrar | Team size | 6
Team member E | Student Accounts Specialist | Individual contributor | Student Accounts | Cross-level check | Good. All three levels are in the room.
Team member F | Admissions Operations Lead | Supervisor | Admissions | Departments represented | 4

## Impact Estimate
Impact Estimate
What fixing the top pick is worth. Replace the tan example values with your own.
Project | Financial aid verification takes too long
Requests handled per year | 2400 | From your system or a month's count times 12.
Turnaround now (days) | 14 | Median days from request to done.
Target turnaround (days) | 5
Staff minutes per request now | 40 | Hands-on time, not waiting time.
Staff minutes per request after | 25
Loaded hourly staff cost ($) | 38 | Wage plus benefits.
Paid hours per full-time employee per year | 2080
Days faster per request | 9
Staff hours freed per year | 600
Value of staff time freed per year | 22800 | Time your staff gets back for students, not a budget cut.
Full-time equivalents freed | 0.28846
Improvement in turnaround | 64.29%
Student-days of waiting removed per year | 21600

## Formula Guide
Formula Guide
Every calculated cell in this workbook, what it does, and how to rebuild or extend it.
Tab | Cell(s) | What it calculates | Formula (first cell) | To extend
Schedule | B7 | 3 or 6 sessions, from the format. | =IF(B5="Six 1-hour sessions",6,3)
Schedule | B8 | Six live hours split across the sessions. | =6/B7
Schedule | B9 | Check. Should always be 6. | =B7*B8
Schedule | B10 | Date of the last session. | =IF(COUNT(B14:B19)=0,"",MAX(B14:B19))
Schedule | B11 | Weeks from kickoff to the final session. | =IF(B10="","",ROUND((B10-B4)/7,0))
Schedule | A14:A19 | Session number, shown only up to the number of sessions. | =IF(ROW()-13<=$B$7,ROW()-13,"") | Six rows cover both formats. Rows beyond the session count stay blank.
Schedule | B14:B19 | Kickoff plus the weeks between sessions. WORKDAY(date-1,1) moves a weekend date to the next weekday. | =IF(A14="","",WORKDAY($B$4+(A14-1)*$B$6*7-1,1)) | Six rows cover both formats. Rows beyond the session count stay blank.
Schedule | C14:C19 | Hours for this session. | =IF(A14="","",$B$8) | Six rows cover both formats. Rows beyond the session count stay blank.
Schedule | D14:D19 | Picks the agenda for this session from the 3-session or 6-session column. | =IF(A14="","",IF($B$7=3,INDEX($H$14:$H$19,A14),INDEX($I$14:$I$19,A14))) | Six rows cover both formats. Rows beyond the session count stay blank.
Schedule | E14:E19 | Picks the between-session team work the same way. | =IF(A14="","",IF($B$7=3,INDEX($J$14:$J$19,A14),INDEX($K$14:$K$19,A14))) | Six rows cover both formats. Rows beyond the session count stay blank.
Project Picker | A7:A16 | Candidate number. | =IF(B7="","",ROW()-6) | Filled to row 16. For more candidates, insert rows above row 16 and copy down.
Project Picker | H7:H16 | Each score times its weight, added up. | =IF(B7="","",SUMPRODUCT(C7:G7,$C$5:$G$5)) | Filled to row 16. For more candidates, insert rows above row 16 and copy down.
Project Picker | I7:I16 | Rank, highest score first. The COUNTIF part breaks ties so no two candidates share a rank. | =IF(H7="","",RANK(H7,$H$7:$H$16)+COUNTIF($H$7:H7,H7)-1) | Filled to row 16. For more candidates, insert rows above row 16 and copy down.
Project Picker | J7:J16 | Marks the top-ranked candidates, as many as the Teams number. | =IF(I7="","",IF(I7<=$B$3,"Pick","")) | Filled to row 16. For more candidates, insert rows above row 16 and copy down.
Project Picker | C18 | The candidate ranked 1. | =IFERROR(INDEX(B7:B16,MATCH(1,I7:I16,0)),"")
Project Picker | C19 | All weights times the top score of 5. | =SUM(C5:G5)*5
Project Picker | C20 | Top score divided by the highest possible score. | =IFERROR(MAX(H7:H16)/C19,"")
Team | G5:G7 | People at this level. | =COUNTIF($C$5:$C$20,F5)
Team | G8 | Counts names listed. | =COUNTA(A5:A20)
Team | G9 | Confirms supervisors, managers, and individual contributors are all represented, and names the missing level if not. | =IF(AND(G5>0,G6>0,G7>0),"Good. All three levels are in the room.","Add at least one "&IF(G5=0,"supervisor",IF(G6=0,"manager","individual contributor"))&".")
Team | G10 | Counts distinct departments. Each department adds up to exactly 1. | =SUMPRODUCT((D5:D20<>"")/COUNTIF(D5:D20,D5:D20&""))
Impact Estimate | B4 | The top pick from Project Picker. | ='Project Picker'!C18
Impact Estimate | B12 | Turnaround now minus target. | =B6-B7
Impact Estimate | B13 | Requests times minutes saved, in hours. | =B5*(B8-B9)/60
Impact Estimate | B14 | Hours freed times hourly cost. | =B13*B10
Impact Estimate | B15 | Hours freed divided by paid hours per employee. | =IF(B11=0,"",B13/B11)
Impact Estimate | B16 | Days saved as a share of today's turnaround. | =IF(B6=0,"",B12/B6)
Impact Estimate | B17 | Requests times days faster. | =B5*B12